## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
DataBase
| ReDevelop Task Schema | 5 | Youssef Shalaby | Amr Nashaat | Mohammed Islam | Key | Member | tasks
| ReDevelop Consultancy Agency Schema | 5 | Youssef Shalaby | Mohammed Mahmoud | Yara Khaled | New
| ReDevelop Partner Schema | 5 | Youssef Shalaby | Farah Abdelsalam | Ali Zamzamy | Tweak
| ReDevelop User Schema | 5 | Mohammed Mahmoud | Youssef Shalaby | Farah Abdelsalam
| ReDevelop User Schema | 5 | Mohammed Mahmoud | Youssef Shalaby | Farah Abdelsalam
| ReDevelop Location Schema |  | Seif Demerdash | Youssef Shalaby | Farah Abdelsalam
| ReDevelop Event Schema | 5 | Youssef Shalaby | Amr Nashaat | Ali Zamzamy | Not Needed | Youssef Shalaby | 13
BackEnd ReAdjustments and New Logic | [6 empty] | Seif Demerdash | 7
1.1 | (Partner) I can submit a description (including an estimated effort/time needed, level of commitment, experience/skills needed, monetary compensation,consultancy assigned to it++ ) of a task/project so that it can be posted. | 5 | Youssef Shalaby | Amr Nashaat | Farah Abdelsalam |  | Amr Nashaat | 6
1.2 | (Partner) I can post tasks and projects, so that candidates can apply. (after approval) | 5 | Ali Zamzamy | Youssef Shalaby | Farah Abdelsalam |  | Ali Zamzamy | 6
1.3 | (Admin) I can check description of task/project and negotiate with partner, so that it’s made sure that it has all needed attributes | 5 | Amr Nashaat | Youssef Shalaby | Farah Abdelsalam |  | Mohammed Mahmoud | 6
1.4 | (Member) I can view and search posted tasks, so that I can apply if eligible I have the required skills for the task | 5 | Youssef Shalaby | Amr Nashaat | Farah Abdelsalam |  | Engy Kamel | 5
1.5 | (Admin) I want to notify accepted candidate that they’re accepted and send a task orientation invitation | 5 | Modified in Sprint6 |  |  |  | Farah Abdelsalam | 5
1.6 | (Admin) I can see all applicants on all tasks, so that I can decide who will be assigned to the task. | 5 | Mohammed Islam | Youssef Shalaby | Ali Zamzamy |  | Mohammed Islam | 4
1.7 | (Consultany Agency) I can see all applicants on all tasks, so that I can decide who will be assigned to the task. | 5 | Amr Nashaat | Youssef Shalaby | Mohammed Islam |  | Yara Khaled | 3
1.8 | (Partner) Add Tasks to my Project | 5 | Youssef Shalaby | Amr Nashaat | Mohammed Islam |  | Mohammed Hossam | 3
1.epic | (Member) want to view recommendations of tasks that match my skills. | 5 | Youssef Shalaby | Farah Abdelsalam | Ali Zamzamy |  | Ramy Beleihy | 1
1.9 | (Partner) I can Create Project | 5 | Youssef Shalaby | Farah Abdelsalam | Ali Zamzamy
1.1 | (Member) I can Cancel my Application | 5 | Amr Nashaat | Farah Abdelsalam | Ali Zamzamy
1.11 | (Member) I can View All The Tasks I applied on | 5 | Ali Zamzamy | Farah Abdelsalam | Mohammed Islam |  | Member | Reviews
1.12 | (Consultancy Agency) I can Apply on a project | 5 | Farah Abdelsalam | Youssef Shalaby | Mohammed Islam |  | Youssef Shalaby | 18
1.13 | (Consultancy Agency) I can Cancell my Application on a project | 5 | Farah Abdelsalam | Youssef Shalaby | Ali Zamzamy |  | Ali Zamzamy | 17
1.14 | (Consultancy Agency) I can View all The projects I'm invloved in | 5 | Mohammed Islam | Youssef Shalaby | Ali Zamzamy |  | Mohammed Islam | 15
1.15 | (Consultancy Agency) I can View all The Tasks I'm invloved in | 5 | Amr Nashaat | Youssef Shalaby | Ali Zamzamy |  | Amr Nashaat | 14
2.4 &2.5 | (Member & Partner) I can or cannot apply for a live event. |  | Engy Kamel | Yara Khaled | Mohammed Mahmoud |  | Farah Abdelsalam | 12
2.6 | (Partner) I should be able to receive feedback from attendees after each event. |  | Yara Khaled | Engy Kamel | Ramy Beleihy |  | Mohammed Mahmoud | 9
2.12 | As an admin I should be able to view all not accepted events |  | Engy Kamel | Mohammed Mahmoud | Ramy Beleihy |  | Yara Khaled | 7
2.13 | As an admin I should be able to accept or respons to not accepted events |  | Mohammed Mahmoud | Seif Demerdash | Ramy Beleihy |  | Engy Kamel | 6
2.14 | As an Admin i should be able to create a Location with its sub locations and places |  | Seif Demerdash | Engy Kamel | Mohammed Mahmoud |  | Ramy Beleihy | 5
2.15 | As a partner or consultancy who initiated an Event or admin I should be able to accept an applicant to attend an event |  | Seif Demerdash | Mohammed Hossam | Yara Khaled |  | Seif Demerdash | 3
- | ReDevelop Event CRUDs |  | Mohammed Hossam | Mohammed Mahmoud | Engy Kamel |  | Mohammed Hossam | 4
2.epic | (Partner & Member) I should be recommended events based on my interest/ attended events and locations. |  | Mohammed Mahmoud | Yara Khaled | Mohammed Islam
FrontEnd
10.1 | Update Components for Story 1.1 | 3 | Youssef Shalaby | Ali Zamzamy | Amr Nashaat
10.2 | Update Components for Story 1.2 | 3 | Ali Zamzamy | Amr Nashaat | Mohammed Islam
10.3 | Update Componenrs for Story 1.3 | 3 | Amr Nashaat | Mohammed Islam | Youssef Shalaby
10.4 | Update Componenrs for Story 1.6 | 3 | Mohammed Islam | Youssef Shalaby | Ali Zamzamy
10.7 | Develop React Components For task 2.1 from Sprints 1 and 2 | 4 | Mohammed Hossam | Mohammed Islam | Ramy Beleihy
10.8 | Develop React Components For task 2.2 from Sprints 1 and 2 | 4 | Seif Demerdash | Mohammed Hossam | Ali Zamzamy
10.9 | Develop React Components For task 2.3 from Sprints 1 and 2 | 4 | Mohamed Mahmoud | Seif Demerdash | Yara Khaled
10.1 | Develop React Components For task 2.4&2.5 from Sprints 1 and 2 | 4 | Engy Kamel | Mohammed Mahmoud | Seif Demerdash
10.11 | Develop React Components For task 2.6 from Sprints 1 and 2 | 4 | Yara Khaled | Engy Kamel | Amr Nashaat |  | avergae tasks per person | 6.1111
10.12 | Develop React Components For task 2.7 from Sprints 1 and 2 | 4 | Ramy Beleihy | Yara Khaled | Engy Kamel |  | average review per person | 11.4444
10.13 | Develop Components (UX) for Story 1.4 | 4 | Youssef Shalaby | Ali Zamzamy | Amr Nashaat
10.14 | Develop Components (UX) for Story 1.7 | 4 | Ali Zamzamy | Amr Nashaat | Mohammed Islam
10.15 | Develop Components (UX) for Story 1.8 | 4 | Amr Nashaat | Mohammed Islam | Youssef Shalaby
10.16 | Develop Components (UX) for Story 1.9 | 4 | Mohammed Islam | Youssef Shalaby | Ali Zamzamy
10.17 | Develop Components (UX) for Story 1.10 | 4 | Youssef Shalaby | Ali Zamzamy | Amr Nashaat
10.18 | Develop Components (UX) for Story 1.11 | 4 | Ali Zamzamy | Amr Nashaat | Mohammed Islam
10.19 | Develop Components (UX) for Story 1.12 | 4 | Farah Abdelsalam | Mohammed Islam | Youssef Shalaby
10.2 | Develop Components (UX) for Story 1.13 | 4 | Farah Abdelsalam | Youssef Shalaby | Ali Zamzamy
10.21 | Develop Components (UX) for Story 1.14 | 4 | Youssef Shalaby | Ali Zamzamy | Amr Nashaat
10.22 | Develop Components (UX) for Story 1.15 | 4 | Ali Zamzamy | Amr Nashaat | Mohammed Islam
10.23 | Develop Components (UX) for Story 1.Epic | 4 | Farah Abdelsalam | Mohammed Islam | Youssef Shalaby
10.24 | Develop Components (UX) for Story 2.12 | 4 | Engy Kamel | Mohammed Hossam | Mohammed Mahmoud
10.25 | Develop Components (UX) for Story 2.13 | 4 | Mohammed Mahmoud | Engy Kamel | Yara Khaled
10.26 | Develop Components (UX) for Story 2.14 | 4 | Seif Demerdash | Mohammed Mahmoud | Ramy Beleihy
10.27 | Develop Components (UX) for Story 2.15 | 4 | Seif Demerdash | Mohammed Mahmoud | Mohammed Hossam
10.28 | Filter by price | 4 | Mohammed Hossam | Seif Demerdash | Engy Kamel
10.29 | Filter by location | 4 | Seif Demerdash | Mohammed Hossan | Mohammed Hossam
10.3 | Filter by places | 4 | Yara Khaled | Seif Demerdash | Mohammed Hossam
10.31 | Filter by topics | 4 | Mohammed Mahmoud | Yara Khaled | Mohammed Hossam
10.32 | Filter by Speakers | 4 | Engy Kamel | Mohammed Mahmoud | Mohammed Hossam