## Sheet1
Team name | A Team | Guidelines | 1. Sort the user stories according to priority | key:
Project | Lirten Hub |  | 2. Priority refers to how fundamental is the user story for the project ( For example : you cannot implement Sumerge without "add investor" user story ) | DONE
Module | Task Management/Live Events |  | 3. For everyone: Registration and log-in will be implemented in later sprints (~ Sprint 3) - this is when we will cover this material in Labs
Scrum ID | 40-808 |  | 4. Use the unique ID to structure the user stories. For example: If (1) is "Portfolio Development" module, then 1.1 and 1.2 … are the related user stories
Scrum Email | Youshalaby@gmail.com |  | 5. Only features to be implemented in later sprints can be left as epics.
Uniuqe ID | User story | Epic ? | Priority (high/medium/low)
1 | Task Management
1.1 | (Partner) I can submit a description (including an estimated effort/time needed, level of commitment, experience/skills needed, monetary compensation,consultancy assigned to it++ ) of a task/project so that it can be posted. |  | high
1.2 | (Partner) I can post tasks and projects, so that candidates can apply. |  | high
1.3 | (Admin) I can check description of task/project and negotiate with partner, so that it’s made sure that it has all needed attributes |  | high
1.4 | (Member) I can view and search posted tasks, so that I can apply if eligible I have the required skills for the task |  | medium
1.5 | (Admin) I want to notify accepted candidate that they’re accepted and send a task orientation invitation
1.6 | (Admin) I can see all applicants on all tasks, so that I can decide who will be assigned to the task. |  | medium
1.7 | (Consultany Agency) I can see all applicants on all tasks, so that I can decide who will be assigned to the task. |  | medium
1.epic | (Member) want to view recommendations of tasks that match my skills. |  | low
2 | Live Events
2.1 | (Partner) I should be able to initiate a request to organize an event and submit it. N.B: requests can be to organize the event by partner or by Lirten-Hub itself. |  | High
2.2 | (Member) I should be allowed to book an available and offered place . |  | High
2.3 | (Member) I should be able to view any event according to its type. |  | Medium
2.4 | (Member) I can or cannot apply for a live event. |  | Medium
2.5 | (Partner) I can or cannot apply for a live event. |  | Medium
2.6 | (Partner) I should be able to receive feedback from attendees after each event. |  | Medium
2.7 | (Partner) I can view an event based on the event’s location, description, registration price, remaining places, speakers and topics. |  | Low
2.8 | (Member) I can view an event based on the event’s location, description, registration price, remaining places, speakers and topics. |  | Low
2.9 | (Member) who attended an event, the event attended must be added to my history of attended events in my profile. |  | Low
2.11 | (Member) after each event, I should be prompted with a form where I can rate the event and send any feedback to the organizing entity. |  | Low
2.epic | (Partner) I should be recommended events based on my interest/ attended events and locations. |  | Low
2.epic2 | (Member) I should be recommended events based on my interest/ attended events and locations. |  | Low
3 | Login and Registration
3.1 | (Member, Partner & Consultancy Agency) should be able to elete my attributes. |  | low
3.2 | (Member, Partner & Consultancy Agency) should be able to login. |  | low
3.3 | (Member, Partner & Consultancy Agency) should be able to logout. |  | low
3.4 | (Member, Partner & Consultancy Agency) should be able to Browse through Lirten Hub |  | low
3.5 | (Member, Partner & Consultancy Agency) I should be able to sign-up |  | low
3.6 | (Member, Partner & Consultancy Agency) should be able delete my attributes. |  | low
3.7 | (Admin) Accept or Reject Profile Edits By the users |  | low
4 | Data Management and Reconstructing
4.1 | Redevlop Task and Project Relation |  | high
4.2 | Develop Consultancy Agency Sponsoring Mechanism |  | high
4.3 | Re-adjust User Entity Array to Mongo Schema |  | medium
4.4 | Re-adjust Task Entity Array to Mongo Schema |  | medium
4.5 | Re-adjust Event Entity Array to Mongo Schema |  | medium
4.6 | Re-adjust Location Entity Array to Mongo Schema |  | medium
4.7 | Re-adjust Member Entity Array to Mongo Schema |  | medium
4.8 | Re-adjust Partner Entity Array to Mongo Schema |  | medium
4.9 | Re-adjust Consultancy Agency Entity Array to Mongo Schema |  | medium
4.1 | Re-Fit/Integrate the task Orientation Enitity |  | medium
4.11 | Re-Fit/Integrate Notfication Enitity |  | medium
4.12 | Re-Fit/Integrate Request Entities |  | medium
5 | CRUD Redevolpment using a DataBase
5.1 | User CRUD |  | high
5.2 | Task CRUD |  | high
5.3 | Event CRUD |  | high
5.4 | Member CUD |  | high
5.5 | Location CRUD |  | high
5.6 | Partner CRUD |  | high
5.7 | Consultancy Agency CRUD |  | high
5.8 | Task Orientation/ Notfication CRUD (OPTIONAL) |  | low
6 | Task Component Story re-adjustments
6.1 | ReAdjust Story 1.1 on Mongo Schema |  | medium
6.2 | ReAdjust Story 1.2 on Mongo Schema |  | medium
6.3 | ReAdjust Story 1.3 on Mongo Schema |  | medium
6.4 | ReAdjust Story 1.5 on Mongo Schema |  | medium
6.5 | ReAdjust Story 1.6 on Mongo Schema |  | medium
7 | Event Component Story re-adjustments
7.1 | ReAdjust Story 2.1 on Mongo Schema |  | medium
7.2 | ReAdjust Story 2.2 on Mongo Schema |  | medium
7.3 | ReAdjust Story 2.3 on Mongo Schema |  | medium
7.4 | ReAdjust Story 2.4 on Mongo Schema |  | medium
7.5 | ReAdjust Story 2.5 on Mongo Schema |  | medium
7.6 | ReAdjust Story 2.6 on Mongo Schema |  | medium
7.7 | ReAdjust Story 2.17 on Mongo Schema |  | medium