## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
2.8 | (Member) who attended an event, the event attended must be added to my history of attended events in my profile. | 4 | Yara Khaled | Mohammed Mahmoud | Seif Demerdash
4.1 | Redevlop Task and Project Relation | 5 | Youssef Shalaby | Farah Abdelsalam | Ali Zamzamy
4.2 | Develop Consultancy Agency Sponsoring Mechanism | 5 | Youssef Shalaby | Farah Abdelsalam | Amr Nashaat
4.3 | Re-adjust User Entity Array to Mongo Schema | 3 | Mohammed Mahmoud | Yara Khaled | Mohammed Hossam
4.4 | Re-adjust Task Entity Array to Mongo Schema | 3 | Youssef Shalaby | Amr Nashaat | Mohammed Islam | 1 | min
4.5 | Re-adjust Event Entity Array to Mongo Schema | 3 | Mohammed Mahmoud | Mohammed Hossam | Yara Khaled | 5 | max
4.6 | Re-adjust Location Entity Array to Mongo Schema | 3 | Seif Demerdash | Mohammed Mahmoud | Engy Kamel
4.7 | Re-adjust Member Entity Array to Mongo Schema | 3 | Mohammed Islam | Youssef Shalaby | Mohammed Mahmoud
4.8 | Re-adjust Partner Entity Array to Mongo Schema | 3 | Ali Zamzamy | Ramy Beleihy | Mohammed Islam
4.9 | Re-adjust Consultancy Agency Entity Array to Mongo Schema | 3 | Yara Khaled | Youssef Shalaby | Amr Nashaat
4.1 | Re-Fit/Integrate the task Orientation Enitity | 2 | Farah Abdelsalam | Youssef Shalaby | Amr Nashaat
4.11 | Re-Fit/Integrate Notfication Enitity | 2 | Farah Abdelsalam | Youssef Shalaby | Amr Nashaat |  |  | Member | tasks
4.12 | Re-Fit/Integrate Request Entities | 3 | Mohammed Hossam | Mohammed Mahmoud | Seif Demerdash
[8 empty] | Mohammed Mahmoud | 4
5.1 | User CRUD | 4 | Mohammed Mahmoud | Engy Kamel | Yara Khaled |  |  | Youssef Shalaby | 4
5.2 | Task CRUD | 4 | Amr Nashaat | Youssef Shalaby | Ali Zamzamy |  |  | Farah Abdelsalam | 4
5.3 | Event CRUD | 4 | Mohammed Mahmoud | Mohammed Hossam | Yara Khaled |  |  | Engy Kamel | 3
5.4 | Member CUD | 4 | Engy Kamel | Seif Demerdash | Yara Khaled |  |  | Yara Khaled | 3
5.5 | Location CRUD | 4 | Seif Demerdash | Seif Demerdash | Farah Abdelsalam |  |  | Amr Nashaat | 3
5.6 | Partner CRUD | 4 | Ramy Beleihy | Seif Demerdash | Ramy Beleihy |  |  | Mohammed Hossam | 3
5.7 | Consultancy Agency CRUD | 4 | Amr Nashaat | Farah Abdelsalam | Mohammed Hossam |  |  | Seif Demerdash | 3
5.8 | Task Orientation/ Notfication CRUD (OPTIONAL) | 1 | Farah Abdelsalam | Amr Nashaat | Mohammed Islam |  |  | Ramy Beleihy | 2
[8 empty] | Mohammed Islam | 2
6.1 | ReAdjust Story 1.1 on Mongo Schema | 4 | Youssef Shalaby | Farah Abdelsalam | Ali Zamzamy |  |  | Ali Zamzamy | 2
6.2 | ReAdjust Story 1.2 on Mongo Schema | 4 | Ali Zamzamy | Youssef Shalaby | Mohammed Islam
6.3 | ReAdjust Story 1.3 on Mongo Schema | 4 | Amr Nashaat | Farah Abdelsalam | Ali Zamzamy
6.4 | ReAdjust Story 1.5 on Mongo Schema | 4 | Farah Abdelsalam | Mohammed Islam | Amr Nashaat
6.5 | ReAdjust Story 1.6 on Mongo Schema | 4 | Mohammed Islam | Ali Zamzamy | Farah Abdelsalam
[8 empty] | Member | Reviews
7.1 | ReAdjust Story 2.1 on Mongo Schema | 4 | Mohammed Hossam | Mohammed Mahmoud | Engy Kamel |  |  | Amr Nashaat | 7
7.2 | ReAdjust Story 2.2 on Mongo Schema | 4 | Seif Demerdash | Mohammed Hossam | Engy Kamel |  |  | Mohammed Mahmoud | 7
7.3 | ReAdjust Story 2.3 on Mongo Schema | 4 | Mohammed Hossam | Mohammed Mahmoud | Engy Kamel |  |  | Farah Abdelsalam | 7
7.4 | ReAdjust Story 2.4 on Mongo Schema | 4 | Engy Kamel | Yara Khaled | Ali Zamzamy |  |  | Youssef Shalaby | 6
7.5 | ReAdjust Story 2.5 on Mongo Schema | 4 | Engy Kamel | Yara Khaled | Sief Demerdash |  |  | Mohammed Hossam | 6
7.6 | ReAdjust Story 2.6 on Mongo Schema | 4 | Yara Khaled | Engy Kamel | Ramy Beleihy |  |  | Engy Kamel | 6
7.7 | ReAdjust Story 2.17 on Mongo Schema | 4 | Ramy Beleihy | Mohammed Mahmoud | Mohammed Hossam |  |  | Ali Zamzamy | 6
[8 empty] | Seif Demerdash | 5
[8 empty] | Yara Khaled | 5
[8 empty] | Mohammed Islam | 5
[8 empty] | Ramy Beleihy | 3