## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 |  |  | key
1.4 | (Member) I can view and search posted tasks, so that I can apply if eligible I have the required skills for the task | 3 | Youssef Shalaby | Mohammed Hossam | Amr Nashaat |  |  | Edited
1.7 | (Consultany Agency) I can see all applicants on all tasks, so that I can decide who will be assigned to the task. | 3 | Mohammed Hossam | Mohammed Islam | Youssef Shalaby |  |  | Added
1.epic | (Member) want to view recommendations of tasks that match my skills. | 3 | Youssef Shalaby | Mohammed Mahmoud | Amr Nashaat |  |  | Member | tasks
|  | 5 | [5 empty] | Youssef Shalaby | 5
2.9 | (Member) who attended an event, the event attended must be added to my history of attended events in my profile. | 5 | Mohammed Mahmoud | Seif Demerdash | Yara Khaled |  |  | Farah Abdelsalam | 3
2.11 | (Member) after each event, I should be prompted with a form where I can rate the event and send any feedback to the organizing entity. | 3 | Yara Khaled | Mohammed Mahmoud | Engy Kamel |  |  | Engy Kamel | 3
[8 empty] | Amr Nashaat | 3
5.6 | Partner Entity CRUD | 5 | Ali Zamzamy | Youssef Shalaby | Mohammed Hossam |  |  | Mohammed Mahmoud | 3
[8 empty] | Yara Khaled | 3
8.1 | Develop unit tests for User CRUD | 5 | Mohammed Mahmoud | Youssef Shalaby | Mohammed Hossam |  |  | Mohammed Hossam | 3
8.2 | Develop unit tests for Task CRUD | 5 | Amr Nashaat | Youssef Shalaby | Farah Abdelsalam |  |  | Seif Demerdash | 3
8.3 | Develop unit tests for Event CRUD | 5 | Mohammed Mahmoud | Seif Demerdash | Engy Kamel |  |  | Ali Zamzamy | 3
8.4 | Develop unit tests for Member CUD | 5 | Engy Kamel | Mohammed Islam | Amr Nashaat |  |  | Ramy Beleihy | 1
8.5 | Develop unit tests for Location CRUD | 5 | Seif Demerdash | Ramy Beleihy | Yara Khaled |  |  | Mohammed Islam | 2
8.6 | Develop unit tests for Consultancy Agency CRUD | 5 | Amr Nashaat | Mohammed Hossam | Youssef Shalaby | 1 | min
8.7 | Develop unit tests for Project Entity CRUD | 5 | Youssef Shalaby | Mohammed Mahmoud | Farah Abdelsalam | 5 | max
8.8 | Develop unit tests for Partner Entity CRUD | 5 | Farah Abdelsalam | Yara Khaled | Amr Nashaat |  |  | Member | Reviews
8.9 | Develop unit tests for Story 1.1 | 4 | Youssef Shalaby | Ali Zamzamy | Amr Nashaat |  |  | Youssef Shalaby | 5
8.1 | Develop unit tests for Story 1.2 | 4 | Ali Zamzamy | Mohammed Islam | Farah Abdelsalam |  |  | Yara Khaled | 6
8.11 | Develop unit tests for Story 1.3 | 4 | Amr Nashaat | Farah Abdelsalam | Mohammed Islam |  |  | Seif Demerdash | 6
8.12 | Develop unit tests for Story 1.5 | 4 | Farah Abdelsalam | Mohammed Islam | Ali Zamzamy |  |  | Ramy Beleihy | 3
8.13 | Develop unit tests for Story 1.6 | 4 | Mohammed Islam | Amr Nashaat | Ali Zamzamy |  |  | Mohammed Mahmoud | 8
8.14 | Develop unit tests for Story 1.8 | 4 | Youssef Shalaby | Farah Abdelsalam | Ali Zamzamy |  |  | Mohammed Islam | 5
8.15 | Develop unit tests for Story 2.1 | 4 | Mohammed Hossam | Seif Demerdash | Mohammed Mahmoud |  |  | Mohammed Hossam | 7
8.16 | Develop unit tests for Story 2.2 | 4 | Seif Demerdash | Mohammed Hossam | Yara Khaled |  |  | Farah Abdelsalam | 5
8.17 | Develop unit tests for Story 2.3 | 4 | Mohammed Hossam | Mohammed Mahmoud | Engy Kamel |  |  | Engy Kamel | 6
8.18 | Develop unit tests for Story 2.4 | 4 | Engy Kamel | Mohammed Hossam | Ramy Beleihy |  |  | Amr Nashaat | 7
8.19 | Develop unit tests for Story 2.5 | 4 | Engy Kamel | Yara Khaled | Seif Demerdash |  |  | Ali Zamzamy | 5
8.2 | Develop unit tests for Story 2.6 | 4 | Yara Khaled | Seif Demerdash | Engy Kamel
8.21 | Develop unit tests for Story 2.8 | 4 | Yara Khaled | Seif Demerdash | Mohammed Mahmoud
8.22 | Develop unit tests for Story 2.17 | 4 | Ramy Beleihy | Mohammed Mahmoud | Engy Kamel |  |  | avergae tasks per person | 2.9091
8.23 | Develop unit tests for Story 3.2 | 4 | Farah Abdelsalam | Yara Khaled | Ali Zamzamy |  |  | average review per person | 5.7273
8.24 | Develop unit tests for Story 1.7 | 4 | Mohammed Islam | Amr Nashaat
8.25 | Develop unit tests for Story 2.9 | 4 | Seif Demerdash | Mohammed Mahmoud | Engy Kamel
8.26 | Develop unit tests for Story 2.11 | 4 | Ali Zamzamy | Ramy Beleihy | Mohammed Hossam
8.27 |  | 4